## Sheet1
Sprint | Task | Assignee | Status | Start Date | Due Date
Sprint 1: Setup & Core Backend | Set up GitHub repository and project folders | You | Not Started | 2025-05-28 | 2025-05-28
Sprint 1: Setup & Core Backend | Install and configure Python environment | You | Not Started | 2025-05-28 | 2025-05-29
Sprint 1: Setup & Core Backend | Install FastAPI and test basic API | You | Not Started | 2025-05-28 | 2025-05-30
Sprint 1: Setup & Core Backend | Implement /upload API endpoint (accept file) | You | Not Started | 2025-05-28 | 2025-05-31
Sprint 1: Setup & Core Backend | Test file saving locally and log task ID | You | Not Started | 2025-05-28 | 2025-06-01
Sprint 2: OCR Integration & JSON Output | Integrate EasyOCR for text extraction | You | Not Started | 2025-06-04 | 2025-06-04
Sprint 2: OCR Integration & JSON Output | Add preprocessing using OpenCV (grayscale, denoise) | You | Not Started | 2025-06-04 | 2025-06-05
Sprint 2: OCR Integration & JSON Output | Parse OCR results into key-value pairs | You | Not Started | 2025-06-04 | 2025-06-06
Sprint 2: OCR Integration & JSON Output | Implement /result endpoint (return JSON) | You | Not Started | 2025-06-04 | 2025-06-07
Sprint 2: OCR Integration & JSON Output | Test flow end-to-end with sample invoice | You | Not Started | 2025-06-04 | 2025-06-08
Sprint 3: UI + Hosting + RPA Hooks | Create simple HTML+JS frontend for upload | You | Not Started | 2025-06-11 | 2025-06-11
Sprint 3: UI + Hosting + RPA Hooks | Connect frontend to backend API | You | Not Started | 2025-06-11 | 2025-06-12
Sprint 3: UI + Hosting + RPA Hooks | Add GSheet push script using Python RPA | You | Not Started | 2025-06-11 | 2025-06-13
Sprint 3: UI + Hosting + RPA Hooks | Deploy backend (Render/Railway) and frontend (Vercel) | You | Not Started | 2025-06-11 | 2025-06-14
Sprint 3: UI + Hosting + RPA Hooks | Test complete SaaS flow (upload → output → GSheet) | You | Not Started | 2025-06-11 | 2025-06-15